## ods_material_info_v2
project_no | subsystem | pbs_no | pbs_name | self_or_outsource | supplier_name | is_long_cycle | contract_negotiation_date | contract_negotiation_week | contract_delivery_date | contract_delivery_week | actual_delivery_date | actual_delivery_week | plan_inspect_date | plan_inspect_week | complete_inspect_date | complete_inspect_week | install_date | install_week | dept_owner | control_dept_owner | weekly_progress | affects_major_node | risk_level | risk_content | delay_impact | last_update_time | last_update_week | remark
XM-2026-C01 | 总体分系统 | PBS-C01-001 | 综合控制机机箱 | 自研 | — | 否 | 2026-02-03 | 6 | 2026-04-07 | 15 | 2026-04-06 | 15 | 2026-04-14 | 16 | 2026-04-18 | 16 | 2026-04-25 | 17 | 王工/总体室 | 张总/总体室 | 已完成到货检验并进入装配 | 否 | 低 |  |  | 2026-04-25 | 17
XM-2026-C02 | 控制分系统 | PBS-C02-001 | 飞控控制器样机 | 外协 | 中航智控 | 是 | 2026-03-06 | 10 | 2026-05-08 | 19 | 2026-05-08 | 19 | 2026-05-15 | 20 | 2026-05-19 | 21 | 2026-05-26 | 22 | 陈工/控制室 | 赵总/控制室 | 已完成到货检验并进入装配 | 否 | 低 |  |  | 2026-05-26 | 22
XM-2026-C03 | 动力分系统 | PBS-C03-001 | 动力控制组件 | 外协 | 航天动力 | 是 | 2026-04-03 | 14 | 2026-06-05 | 23 | 2026-06-15 | 25 | 2026-06-12 | 24 | 2026-06-19 | 25 | 2026-06-26 | 26 | 赵工/动力室 | 孙总/动力室 | 第二版快照：已完成到货检验并进入装配 | 否 | 低 |  |  | 2026-06-26 | 26 | 第二版快照：到货事项已闭环
XM-2026-C04 | 制导分系统 | PBS-C04-001 | 制导计算机板卡 | 外协 | 中电十三所 | 是 | 2026-05-04 | 19 | 2026-07-06 | 28 | 2026-07-05 | 27 | 2026-07-13 | 29 | 2026-07-17 | 29 | 2026-07-24 | 30 | 林工/制导室 | 马总/制导室 | 已完成到货检验并进入装配 | 否 | 低 |  |  | 2026-07-24 | 30
XM-2026-C05 | 软件分系统 | PBS-C05-001 | 实时软件构件包 | 自研 | — | 否 | 2026-06-03 | 23 | 2026-08-05 | 32 | 2026-08-05 | 32 | 2026-08-12 | 33 | 2026-08-16 | 33 | 2026-08-23 | 34 | 沈工/软件室 | 胡总/软件室 | 已完成到货检验并进入装配 | 否 | 低 |  |  | 2026-08-23 | 34
XM-2026-C06 | 结构分系统 | PBS-C06-001 | 主承力舱段结构件 | 外协 | 江南机械 | 是 | 2026-07-04 | 27 | 2026-09-05 | 36 | 2026-09-23 | 39 | 2026-09-12 | 37 | 2026-09-27 | 39 | 2026-10-04 | 40 | 周工/结构室 | 吴总/结构室 | 第二版快照：已完成到货检验并进入装配 | 否 | 低 |  |  | 2026-10-04 | 40 | 第二版快照：到货事项已闭环
XM-2026-C07 | 电源分系统 | PBS-C07-001 | 电源管理单元 | 自研 | — | 否 | 2026-08-03 | 32 | 2026-10-05 | 41 | 2026-10-04 | 40 | 2026-10-12 | 42 | 2026-10-16 | 42 | 2026-10-23 | 43 | 宋工/电源室 | 高总/电源室 | 已完成到货检验并进入装配 | 否 | 低 |  |  | 2026-10-23 | 43
XM-2026-C08 | 电子分系统 | PBS-C08-001 | 载荷处理模块 | 外协 | 航电电子 | 是 | 2026-09-03 | 36 | 2026-11-05 | 45 | 2026-11-26 | 48 | 2026-11-12 | 46 | 2026-11-30 | 49 | 2026-12-07 | 50 | 徐工/电子室 | 郑总/电子室 | 第二版快照：已完成到货检验并进入装配 | 否 | 低 |  |  | 2026-12-07 | 50 | 第二版快照：到货事项已闭环
XM-2026-C09 | 测控分系统 | PBS-C09-001 | 测控主机样机 | 自研 | — | 否 | 2026-10-04 | 40 | 2026-12-06 | 49 | 2026-12-07 | 50 | 2026-12-13 | 50 | 2026-12-17 | 51 | 2026-12-24 | 52 | 田工/测控室 | 潘总/测控室 | 已完成到货检验并进入装配 | 否 | 低 |  |  | 2026-12-24 | 52
XM-2026-C10 | 试验分系统 | PBS-C10-001 | 综合试验工装 | 外协 | 航试装备 | 是 | 2026-11-03 | 45 | 2027-01-05 | 1 |  |  | 2027-01-12 | 2 |  |  |  |  | 柳工/试验室 | 曹总/试验室 | 供应商正在加急排产，尚未到货 | 是 | 高 | 综合试验工装到货节奏存在波动 | 影响关键节点交付 | 2027-01-19 | 3 | 与风险台账联动