## ods_tech_state_v2
project_no | tech_state_name | change_item | owner | dept | dept_leader | change_submit_time | change_submit_week | completion_signature | signature_closure_date | signature_closure_week | change_reason | change_category | plan_file_closure_date | plan_file_closure_week | plan_reform_date | plan_reform_week | plan_synced | new_plan_count | review_situation | affected_files | affected_objects | file_signature_status | file_signature_date | file_signature_week | reform_status | reform_date | reform_week | project_manager | last_update_time | last_update_week | filled_by | remark
XM-2026-C01 | 综合控制机 | 综合统筹平台技术状态调整 | 王工 | 总体室 | 张总 | 2026-03-23 | 13 | 是 | 2026-04-02 | 14 | 综合统筹平台关键约束调整，需要更新技术状态与文件 | I | 2026-04-13 | 16 | 2026-05-04 | 19 | 是 | 1 | 已评估评审已通过 | XM-2026-C01-SPEC-001;XM-2026-C01-DRAW-002 | 综合控制机机箱 | 已评估评审，已签署 | 2026-04-06 | 15 | 已落实整改 | 2026-05-04 | 19 | 孙PM | 2026-05-04 | 19 | 王工 | 已纳入技术状态跟踪
XM-2026-C02 | 飞控控制器 | 飞控执行机构技术状态调整 | 陈工 | 控制室 | 赵总 | 2026-04-23 | 17 | 是 | 2026-06-04 | 23 | 飞控执行机构关键约束调整，需要更新技术状态与文件 | II | 2026-05-14 | 20 | 2026-06-04 | 23 | 是 | 2 | 已评估评审已通过 | XM-2026-C02-SPEC-001;XM-2026-C02-DRAW-002 | 飞控控制器样机 | 已评估评审，已签署 | 2026-06-04 | 23 | 已落实整改 | 2026-06-09 | 24 | 陈PM | 2026-06-09 | 24 | 陈工 | 第二版快照：文件签署及整改已闭环
XM-2026-C03 | 动力控制组件 | 姿轨动力系统技术状态调整 | 赵工 | 动力室 | 孙总 | 2026-05-21 | 21 | 是 | 2026-05-31 | 22 | 姿轨动力系统关键约束调整，需要更新技术状态与文件 | III | 2026-06-11 | 24 | 2026-07-02 | 27 | 否 | 1 | 已提出需求，已签署 | XM-2026-C03-SPEC-001;XM-2026-C03-DRAW-002 | 动力控制组件 | 已提出需求，已签署 | 2026-06-04 | 23 | 不涉及 | 2026-06-04 | 23 | 赵PM | 2026-06-04 | 23 | 赵工 | 第二版快照：不涉及整改，签署日作为闭环日期
XM-2026-C04 | 制导计算机 | 惯导制导系统技术状态调整 | 林工 | 制导室 | 马总 | 2026-06-21 | 25 | 是 | 2026-08-04 | 32 | 惯导制导系统关键约束调整，需要更新技术状态与文件 | I | 2026-07-12 | 28 | 2026-08-02 | 31 | 是 | 2 | 已评估评审已通过 | XM-2026-C04-SPEC-001;XM-2026-C04-DRAW-002 | 制导计算机板卡 | 已评估评审，已签署 | 2026-08-04 | 32 | 已落实整改 | 2026-08-09 | 32 | 林PM | 2026-08-09 | 32 | 林工 | 第二版快照：文件签署及整改已闭环
XM-2026-C05 | 实时软件构件 | 实时软件平台技术状态调整 | 沈工 | 软件室 | 胡总 | 2026-07-21 | 30 | 是 | 2026-07-31 | 31 | 实时软件平台关键约束调整，需要更新技术状态与文件 | II | 2026-08-11 | 33 | 2026-09-01 | 36 | 是 | 1 | 已评估评审已通过 | XM-2026-C05-SPEC-001;XM-2026-C05-DRAW-002 | 实时软件构件包 | 已评估评审，已签署 | 2026-08-04 | 32 | 已落实整改 | 2026-09-01 | 36 | 沈PM | 2026-09-01 | 36 | 沈工 | 已纳入技术状态跟踪
XM-2026-C06 | 主承力舱段 | 复合结构组件技术状态调整 | 周工 | 结构室 | 吴总 | 2026-08-21 | 34 | 是 | 2026-09-30 | 40 | 复合结构组件关键约束调整，需要更新技术状态与文件 | III | 2026-09-11 | 37 | 2026-10-02 | 40 | 是 | 2 | 已提出需求，已签署 | XM-2026-C06-SPEC-001;XM-2026-C06-DRAW-002 | 主承力舱段结构件 | 已提出需求，已签署 | 2026-09-30 | 40 | 不涉及 | 2026-10-05 | 41 | 周PM | 2026-10-05 | 41 | 周工 | 第二版快照：文件签署及整改已闭环
XM-2026-C07 | 电源管理单元 | 高可靠电源系统技术状态调整 | 宋工 | 电源室 | 高总 | 2026-09-20 | 38 | 否 |  |  | 高可靠电源系统关键约束调整，需要更新技术状态与文件 | I | 2026-10-11 | 41 | 2026-11-01 | 44 | 是 | 1 | 已提出需求，等待评估评审 | XM-2026-C07-SPEC-001;XM-2026-C07-DRAW-002 | 电源管理单元 | 已提出需求，未评估评审 |  |  | 整改中 |  |  | 宋PM | 2026-10-08 | 41 | 宋工 | 待完成文件签署
XM-2026-C08 | 载荷处理模块 | 电子载荷组件技术状态调整 | 徐工 | 电子室 | 郑总 | 2026-10-21 | 43 | 是 | 2026-10-31 | 44 | 电子载荷组件关键约束调整，需要更新技术状态与文件 | II | 2026-11-11 | 46 | 2026-12-02 | 49 | 是 | 2 | 已评估评审已通过 | XM-2026-C08-SPEC-001;XM-2026-C08-DRAW-002 | 载荷处理模块 | 已评估评审，已签署 | 2026-11-04 | 45 | 已落实整改 | 2026-12-02 | 49 | 徐PM | 2026-12-02 | 49 | 徐工 | 已纳入技术状态跟踪
XM-2026-C09 | 测控主机 | 测控链路系统技术状态调整 | 田工 | 测控室 | 潘总 | 2026-11-21 | 47 | 是 | 2026-12-01 | 49 | 测控链路系统关键约束调整，需要更新技术状态与文件 | III | 2026-12-12 | 50 | 2027-01-02 | 53 | 否 | 1 | 已提出需求，已签署 | XM-2026-C09-SPEC-001;XM-2026-C09-DRAW-002 | 测控主机样机 | 已提出需求，已签署 | 2026-12-05 | 49 | 不涉及 | 2026-12-05 | 49 | 田PM | 2026-12-05 | 49 | 田工 | 第二版快照：不涉及整改，签署日作为闭环日期
XM-2026-C10 | 综合试验工装 | 环境试验保障平台技术状态调整 | 柳工 | 试验室 | 曹总 | 2026-12-21 | 52 | 是 | 2027-02-05 | 5 | 环境试验保障平台关键约束调整，需要更新技术状态与文件 | I | 2027-01-11 | 2 | 2027-02-01 | 5 | 是 | 2 | 已评估评审已通过 | XM-2026-C10-SPEC-001;XM-2026-C10-DRAW-002 | 综合试验工装 | 已评估评审，已签署 | 2027-02-05 | 5 | 已落实整改 | 2027-02-10 | 6 | 柳PM | 2027-02-10 | 6 | 柳工 | 第二版快照：文件签署及整改已闭环